## Sheet1
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Completion Times
A | Describe product |  | 1 | 2 | 3 | X |  |  |  |  | 2
B | Develop marketing strategy |  | 1 | 2 | 4 | X |  |  |  |  | 2
C | Design brochure | A | 2 | 4 | 6 | X |  |  |  |  | 4
D | Develop product prototype
D1 | Requirements analysis | A | 2 | 4 | 8 | X | X | X | X | X | 8
D2 | Software design | D1 | 10 | 16 | 24 |  | X | X | X | X | 24
D3 | System design | D1 | 10 | 16 | 24 |  | X | X | X | X | 24
D4 | Coding | D2, D3 | 10 | 16 | 24 |  | X | X | X | X | 24
D5 | Write documentation | D4 | 2 | 4 | 8 | X |  |  |  |  | 8
D6 | Unit testing | D4 | 16 | 24 | 32 | X | X | X | X | X | 32
D7 | System testing | D6 | 16 | 24 | 32 | X | X | X | X | X | 32
D8 | Package deliverables | D5, D7 | 2 | 4 | 6 | X | X | X | X | X | 2
E | Survey potential market | B, C | 6 | 10 | 16 | X |  |  | X |  | 6
F | Develop pricing plan | D8, E | 1 | 2 | 4 | X |  |  |  |  | 1
G | Develop implementation plan | A, D8 | 1 | 2 | 4 | X |  |  |  |  | 1
H | Write client proposal | F, G | 2 | 4 | 8 | X |  |  |  |  | 2
Rate Card:
| Project Manager | 175
| Data Engineer | 175
| Data Scientist | 175
| Front End Developer | 175
| Back End Developer | 175
Tasks that can be completed in parrallel:
A & B
C& D1
D2 & D3
D5 &D6
Equation:
Precedent Constraints
C = xc > xA +2
D1 = xd1 > xA +2
D2= xd2> xd1+4
D3= xd2> xd3+4
D4=

## Sheet2
task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | Completion Times
Describe product |  | 1 | 2 | 3 | 2
Develop marketing strategy |  | 1 | 2 | 4 | 2
Design brochure | A | 2 | 4 | 6 | 4
Develop product prototype
Requirements analysis | A | 2 | 4 | 8
Software design | D1 | 10 | 16 | 24
System design | D1 | 10 | 16 | 24
Coding | D2, D3 | 10 | 16 | 24
Write documentation | D4 | 2 | 4 | 8
Unit testing | D4 | 16 | 24 | 32
System testing | D6 | 16 | 24 | 32
Package deliverables | D5, D7 | 2 | 4 | 6
Survey potential market | B, C | 6 | 10 | 16
Develop pricing plan | D8, E | 1 | 2 | 4
Develop implementation plan | A, D8 | 1 | 2 | 4
Write client proposal | F, G | 2 | 4 | 8